|  | Reference No.: BatStateU-REC-RES-03 |  |  |  |  |  | Effectivity Date: May 18, 2022 |  |  |  |  |  |  |  |  |  | Revision No.: 03 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| MONITORING TOOL FOR ONGOING RESEARCH PROJECT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Date: September 5, 2025 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Research Project Title: Development of an Online College Research Journal Management System for Batangas State University ARASOF-Nasugbu Campus |  |  |  |  |  |  |  |  | Project Leader: Asst. Prof. DJOANNA MARIE V. SALAC |  |  |  |  |  |  |  |  |
| Total Project Cost: P 147, 148.00 |  |  |  |  |  |  |  |  | Duration: July 2025-July 2026 |  |  |  |  |  |  |  |  |
| - Work Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Activities |  |  | Percent Weight of the Activity | Physical Targets (Quantifiable) |  | Target Date of Completion based on the Approved Work Plan |  |  |  | Actual Accomplishment |  |  |  | *Percentage of the Accomplished Tasks |  | Notable findings or challenges encountered |  |
| - Requirements Gathering |  |  | 10% | 1 set of wireframes/ screen sketches 3 diagrams |  | August 2025 |  |  |  | 1 set of wireframes/ screen sketches 3 diagrams (use case diagram, data flow diagram, and ERD) |  |  |  | 10% |  |  |  |
| - Develop an automated submission system |  |  | 8% | 1 article submission module |  | September 2025 |  |  |  | 1 article submission module was developed |  |  |  | 8% |  |  |  |
| - Setting up email notifications |  |  | 2% | 1 email notification type for submission |  | September 2025 |  |  |  | 1 email notification for submission notification |  |  |  | 2% |  |  |  |
| - Develop algorithm for reviewers matching |  |  | 15% | 1 code module that executes reviewer assignment |  | November 2025 |  |  |  | - |  |  |  | - |  |  |  |
| - Implement automated tracking of review deadline and reminders |  |  | 10% | 1 working module for notification and reminders |  | November 2025 |  |  |  | - |  |  |  | - |  |  |  |
| - Develop options for single /double blind per review |  |  | 5% | 1 code module for implementing anonymity rules |  | December 2025 |  |  |  | - |  |  |  | - |  |  |  |
| - Build a dashboard for editors |  |  | 15% | 1 functional dashboard module |  | February 2026 |  |  |  | - |  |  |  | - |  |  |  |
| - Provide editors with collaboration tools |  |  | 10% | 1 collaboration Module |  | March 2026 |  |  |  | - |  |  |  | - |  |  |  |
| - Incorporate progress indicators for submission visualization |  |  | 5% | 1 Progress Indicator Module |  | April 2026 |  |  |  | - |  |  |  | - |  |  |  |
| - Implement strong data protection and security |  |  | 10% | 1 Audit Log module 100% of user credentials are encrypted 1 backup module |  | May 2026 |  |  |  | - |  |  |  | - |  |  |  |
| - Implement different level of access for different types of users |  |  | 10% | 4 roles (Admin, Editor, Reviewer and Author) |  | June 2026 |  |  |  | - |  |  |  | - |  |  |  |
| Total accomplishment as of __20%____: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| * = (actual accomplishment ÷ physical target) x percent weight of the activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Budget Utilization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Type of Request |  | Details of Request |  |  |  |  |  | Amount Requested |  |  | Actual Amount (Amount disbursed) |  | Budget Utilized (%) |  | Remarks / Challenges Encountered |  |  |
| Purchase Request |  | (Date of PR, PR Number, & Category of Request) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cash Advance |  | (Date Requested, Name of Payee, & Purpose of Cash Advance) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Request of Payment |  | (Date Requested, Name of Payee, & Purpose of Payment) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Prepared by: DJOANNA MARIE V. SALAC Project Leader Date Signed: |  |  |  |  | Monitored by: _____________________________________ Dr. FROILAN G. DESTREZA Head, Research Date Signed: |  |  |  |  |  |  | Reviewed & Evaluated by: ___________________________________ Dr. FROILAN G. DESTREZA Vice Chancellor for Research, Development and Extension Services Date Signed: |  |  |  |  |  |